| Project name : |  |  |
| --- | --- | --- |
| Project No.: |  | Tag No.: |
| Document No.: | REV. : | Date : |

| S. No. | Check Items | Check |  | Remarks |
| --- | --- | --- | --- | --- |
|  |  | YES | NO |  |
|  | Checks for Kick-Off: |  |  |  |
|  | Plan the engineering goals for the first week of the project. |  |  |  |
|  | Mobilize Leads |  |  |  |
|  | Obtain budget and obtain or prepare CTRs |  |  |  |
|  | Understand the technical elements of the Contract (eg scope, milestones, confidentiality) |  |  |  |
|  | Compile list of input data |  |  |  |
|  | Review what we committed to deliver via review of the Proposal |  |  |  |
|  | Plan and conduct kick off meeting with customer |  |  |  |
|  | Establish initial list of technical matters to be addressed during KO meeting |  |  |  |
|  | Expedite receipt of input data and circulate to Leads |  |  |  |
|  | Plan and conduct internal kick off meeting with Leads |  |  |  |
|  | Review past lessons (have someone that learnt the lessons present where possible) |  |  |  |
|  | Map out a basic series of tasks for the period until a project schedule is published |  |  |  |
|  | Obtain templates / standard dwgs / specs / dwg borders from customer |  |  |  |
|  | Understand involvement of any Licensors for process technology |  |  |  |
|  | Plan team building activity with Leads / customer |  |  |  |
|  | Properly understand the scope (eg through Alignment workshops) |  |  |  |
|  | Arrange for site visit |  |  |  |
|  | Checks for Resourcing: |  |  |  |
|  | Ensure Leads are mobilizing their teams per resource histograms |  |  |  |
|  | Understand and cater for the Personnel Approval Form process if one exists |  |  |  |
|  | Get commitment from Location Engineering Manager of availability of resources. |  |  |  |
|  | Establish access to Subject Matter Experts as required |  |  |  |
|  | Be involved in the seating arrangements to facilitate key discipline interactions |  |  |  |
|  | Checks for Interfaces / Stakeholders: |  |  |  |
|  | Understand whether there will be construction representation to contribute to the project |  |  |  |
|  | Understand who the customer's technical focal points are and their availability |  |  |  |
|  | Obtain Project Contacts List and circulate to Leads |  |  |  |
|  | Understand the impacts of any regulatory permitting requirements |  |  |  |
|  | Identify who the project sponsor is in case escalation of issues is needed (normally via PM) |  |  |  |
|  | Checks for Interfaces / Stakeholders: |  |  |  |
|  | Prepare Engineering Plan |  |  |  |
|  | Review existing design documentation (eg FEED package) |  |  |  |
|  | Conduct session with Leads to 'walk' them through the Engineering Plan and Project Execution Plan |  |  |  |
|  | Work with Leads to develop schedule |  |  |  |
|  | Prepare Basis of Design |  |  |  |
|  | Prepare Discipline Design Criteria documents as required |  |  |  |
|  | Organize for Leads to prepare Discipline Context Statements |  |  |  |
|  | Establish the use of the Decision Action Form and Register |  |  |  |
|  | Establish how design related Hazards are going to be recorded by the team |  |  |  |
|  | Understand who is going to facilitate review sessions (eg HAZOP) - internal/customer/external |  |  |  |
|  | Plan timing of early reviews (eg HAZID, Plot Plan Review) |  |  |  |
|  | Ensure Engineering is properly represented at Risk Workshop |  |  |  |
|  | If project management don’t set up an Action Register for the project, set one up for engineering |  |  |  |
|  | Setup up Lessons Learnt Register for progressive capture of lessons on project |  |  |  |
|  | Obtain requirements of final deliverables to support Total Investment Cost estimate from Estimating team |  |  |  |
|  | Checks for Deliverables: |  |  |  |
|  | Establish Deliverables Register |  |  |  |
|  | Agree Document Numbering System with customer |  |  |  |
|  | Establish revision sequence / titles to be used |  |  |  |
|  | Agree what the final deliverables will look like with the customer (through examples) |  |  |  |
|  | Obtain requirements of final deliverables to support Total Investment Cost estimate from Estimating team |  |  |  |
|  | Checks for Engineering Controls: |  |  |  |
|  | Agree on progress gates to be used |  |  |  |
|  | Confirm whether progress is permitted to be claimed progressively between gates |  |  |  |
|  | Understand the Change Control process and inform Leads of its use |  |  |  |
|  | Implement the use of the Key Deliverable Change Notice process once key documents frozen |  |  |  |
|  | Ensure Leads are tasked with doing progress updates |  |  |  |
|  | Have Project Controller prepare Discipline S Curves |  |  |  |
|  | Ensure Project Controller is circulating expenditure / progress info to Leads regularly |  |  |  |
|  | Set up weekly progress meeting |  |  |  |
|  | Checks for Technical Query (TQ) system: |  |  |  |
|  | Send initial list of queries / info needs in table format within 1 wk of KO mtg |  |  |  |
|  | Prepare TQ workflow (i.e. the steps for how the TQ get from the initiator to the licensor / customer, as applicable) |  |  |  |
|  | Agree on TQ distribution |  |  |  |
|  | Set up Template and Register |  |  |  |
|  | Determine need for a system for official instructions from licensor / customer |  |  |  |
|  | Checks for Quality: |  |  |  |
|  | Agree with Quality team need for audits |  |  |  |
|  | Ensure capable people are designated for checking activities |  |  |  |
|  | Ensure stamps are available to team |  |  |  |
|  | Review / customize Discipline Task and Deliverables Plans and append to Eng Plan |  |  |  |
|  | Arrange for a Start-up Peer Review where appropriate |  |  |  |
|  | Schedule in Technical Peer Reviews as required |  |  |  |
|  | Establish engineering templates and store in project folder (e.g. for Reports, data sheets) |  |  |  |
|  | Understand the independent / cold eyes reviews and audits to be done by licensor / customer, as applicable |  |  |  |
|  | Miscellaneous Technical Checks: |  |  |  |
|  | Set up Weight Control system as necessary |  |  |  |
|  | Set up P&ID Legend sheet |  |  |  |
|  | Agree whose data sheets are going to be used (eg customer, other) |  |  |  |
|  | Establish what pipe specs are to be used |  |  |  |
|  | Obtain geotechnical data |  |  |  |
|  | Select International Electric Code (IEC) vs National Electric Code (NEC) |  |  |  |
|  | Select imperial vs metric |  |  |  |
|  | Decide on use of ISO standards (ASME, API) |  |  |  |
|  | Establish need for seismic assessment (and basis) |  |  |  |
|  | Establish need for blast assessment (and basis) |  |  |  |
|  | Decide on type of fatigue analysis to be undertaken |  |  |  |
|  | Decide on Fieldbus vs 4x20mA |  |  |  |
|  | Establish level requirements (e.g. air gap, level of pavement above grade) |  |  |  |
|  | Establish basis of environmental data (wind, wave, current) |  |  |  |
|  | Determine emergency power needs |  |  |  |
|  | Agree number of process simulation cases |  |  |  |
|  | Assess levels of redundancy |  |  |  |
|  | Understand whether modularization / skids are to be adopted |  |  |  |
|  | Plan for the implications of re-use of existing equipment / piping / structures |  |  |  |
|  | Checks for Training: |  |  |  |
|  | Organize any necessary training (systems / processes) |  |  |  |
|  | Arrange any necessary site inductions |  |  |  |
|  | Arrange any necessary security clearances for site access |  |  |  |
|  | Checks for Document Review: |  |  |  |
|  | Agree review period duration that customer will work to (sometimes included in Contract) |  |  |  |
|  | Agree with customer that comments will be consolidated by their focal points where possible |  |  |  |
|  | Prepare Squad Check and Document Distribution Matrix |  |  |  |
|  | Decide on parallel or series review with customer (series preferred) |  |  |  |
|  | Decide on method of circulating documents (e.g. paper, electronic, 'pink' desk for Sq Chk) |  |  |  |
|  | Decide whether electronic red line markup is going to be used |  |  |  |
|  | Determine whether Comment Response Sheets are going to be used |  |  |  |
|  | Checks for Document / Data Management: |  |  |  |
|  | Decide on Document / Data Management system |  |  |  |
|  | Establish handover requirements for documents and data and conduct set up to achieve this |  |  |  |
|  | Resolve how the customer is going to interface into our system |  |  |  |
|  | Organize document workflow (i.e. the steps for how a deliverable gets from author to the customer) |  |  |  |
|  | Decide on filing protocols (electronic, paper, check prints, masters, vendor data, SharePoint etc.) |  |  |  |
|  | Checks for System Decisions: |  |  |  |
|  | Complete Engineering Systems Project Checklist for decisions on systems to be used |  |  |  |
|  | List systems to be used in Eng Plan |  |  |  |
|  | Decide on need for a systems map |  |  |  |
|  | Verify the versions to be used (including any customer requirements) |  |  |  |
|  | For Workshare, establish the systems being used in the Supporting Office |  |  |  |
|  | Understand system costs and recover from customer as appropriate |  |  |  |
|  | Checks for Support: |  |  |  |
|  | Determine what support is needed for set up/admin of the systems |  |  |  |
|  | Establish targeted systems training plan as required |  |  |  |
|  | Review needs for system administration |  |  |  |
|  | Confirm budget for support |  |  |  |
|  | Checks for System 'Integration': |  |  |  |
|  | Understand level of Integration expected from customer (sometimes specified in bid docs) |  |  |  |
|  | Decide on level of Integration between systems that is going to be adopted |  |  |  |
|  | Address skill required in the team for Integration (both at Designer, Admin level) |  |  |  |
|  | Obtain and review Lessons Learnt from past Integration projects |  |  |  |
|  | Checks for Plan 3D model requirements: |  |  |  |
|  | Review requirements of Overall 3D Modeling Procedure & Model Development Guideline |  |  |  |
|  | Establish how 3D model development is going to be conducted |  |  |  |
|  | Decide down to what size piping to be modelled |  |  |  |
|  | Decide detail to which cables are to be run (eg volumes only or trays) |  |  |  |
|  | Establish how model will be divided set up model index) |  |  |  |
|  | Decide whether Structural are fully modelling structures in the 3D model |  |  |  |
|  | Establish who is going to manage the model (Is there a Design Co-Ordinator) |  |  |  |
|  | Determine frequency / method of multi discipline informal model reviews (e.g. weekly) |  |  |  |
|  | Include formal model reviews with customer in Schedule |  |  |  |
|  | Establish how clash checking is going to be conducted |  |  |  |
|  | Develop system for reporting progress of model development |  |  |  |
|  | Miscellaneous Checks: |  |  |  |
|  | Establish responsibility for Underground Services layout (i.e. by Civil or Piping) |  |  |  |
|  | Determine need for laser scanning |  |  |  |
|  | Determine need for surveys (e.g. underground services, topography, tie ins, key points) |  |  |  |
|  | Establish availability of site survey benchmarks / co-ordinate system |  |  |  |
|  | Checks for Engineering Input into Procurement: |  |  |  |
|  | Prepare listing of the packages and what is included / excluded from the packages |  |  |  |
|  | Decide on need for package engineers where complex packages exist |  |  |  |
|  | Ascertain whether client has a vendor listing and obtain |  |  |  |
|  | Understand whether client has global master agreements with vendors and leverage these |  |  |  |
|  | Identify any Long Lead Items and schedule impact on engineering workflow |  |  |  |
|  | Establish owners of each requisition and input needed from other disciplines |  |  |  |
|  | Establish degree of control of budget enquires (e.g. emails or using a template) |  |  |  |

Notes:

- This checklist is no way comprehensive. Based on specific project conditions/equipment some points as deemed necessary can be added / deleted. Addition / deletion of points, if any, needs to be taken up in consultation with Lead Engineer / Technical Specialist / Discipline Manager.

- If     is not filled against any item, please indicate N/A or else provide remarks.

- After release of the respective documents, the completed check list shall be retained by Discipline Engineer for future reference and for technical / quality audit.

- Check points shall be filled by job engineer and checked/approved by Lead/Tech. Specialist.

- The final approved Checklist shall be attached with the respective document if required.

| REV. | SIGN | DATE | SIGN | DATE | REMARKS |
| --- | --- | --- | --- | --- | --- |
|  | JOB ENGINEER |  | LEAD ENGINEER |  |  |